## Transmittal
PROJECT NAME : NJ |  |  | TRANSMITTAL NO: TR-015
FABRICATOR : KS |  |  | DATE: 03/17/2026
Sl. No. | Sheet No. | Drawing Title | Sent for Fabrication |  | Revision History
|  |  | REV# | DATE
E-SHEETS
1 | E201 | MEZZANINE AND | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
2 | E202 | MEZZANINE | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
3 | E203 | LID & LUBE ROOM FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
4 | E204 | CANOPY | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
5 | E205 | CRANE RUNWAY | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
6 | E206 | ROOF FRAMING | 1 | 11-06-2025 | A SRP ISSUED FOR APPROVAL
7 | E207 | ROOF FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
8 | E208 | ROOF MISC FRAMING | 6 | 11-06-2025 | x A SRP ISSUED FOR APPROVAL
9 | E209 | ROOF MISC FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
10 | E210 | ROOF MISC FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
11 | SE201 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
12 | SE202 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
13 | SE203 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
14 | SE204 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
15 | SE205 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
16 | SE206 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
17 | SE207 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
18 | SE208 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
19 | SE209 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
20 | SE210 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
21 | SE211 | ELEVATION VIEW & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
22 | SE220 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
23 | SE221 | SECTION & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
24 | SE222 | SECTION & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
25 | SE223 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
26 | SE224 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
27 | SE225 | SECTIONS | OR | 05-09-2025 | GALVANIZED SURFACE AS REQ'D FOR FIELD WELDING. 0 GSV ISSUED FOR CONSTRUCTION
28 | SE226 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
29 | SE227 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
30 | SE228 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
31 | SE229 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION
32 | SE230 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION