## Transmittal
PROJECT NAME : ST |  |  | TRANSMITTAL NO: TR-013
FABRICATOR : S |  |  | DATE: 03/16/2026
Sl. No. | Sheet No. | Drawing Title | Sent for Fabrication |  | Revision History
|  |  | REV# | DATE
DETAIL SHEETS
1 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication
2 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted
3 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted
4 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
5 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
6 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
7 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
8 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
9 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
10 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
11 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted
12 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted
E-SHEETS
13 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
14 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
15 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
16 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
17 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
18 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
19 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
20 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 08-22-2025 | For Construction 09-25-2025 1 A For Approval
21 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
22 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
23 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 08-22-2025 | For Construction 09-25-2025 3 C For Re-Approval
24 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
25 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
26 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
27 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction
28 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
29 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
30 | E-03.10 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
GATHER SHEET
31 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
32 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
33 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
34 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
35 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
36 | bp1000 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION
37 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION
38 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION
39 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION
40 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED
41 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
42 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
43 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
44 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
45 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
46 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
47 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
48 | pl1517 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
49 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
50 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
51 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
52 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
53 | pl3057 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
54 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
55 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
56 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
57 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
58 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
59 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION