## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 01AR5 | ANCHOR ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01AR5_A.pdf
2 | 01AR4 | ANCHOR ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01AR4_A.pdf
3 | 01B1005 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1005_A.pdf
4 | 01B1006 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1006_A.pdf
5 | 01B1002 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1002_A.pdf
6 | 01B1004 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1004_A.pdf
7 | 01B1003 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1003_A.pdf
8 | 01B1000 | PAINT : GALVANIZED | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1000_A.pdf
9 | 01C1000 | COLUMN DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01C1000_A.pdf
10 | 01B1001 | PAINT : | A | 27-05-2025 | ISSUED FOR APPROVAL | 01B1001_A.pdf
11 | 01AR1 | ANCHOR ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01AR1_A.pdf
12 | 01AR2 | ANCHOR ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01AR2_A.pdf
13 | 01AR3 | ANCHOR ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01AR3_A.pdf
14 | EM09 | DETAILS & ELEVATION VIEW & TYPICAL SECTION | A | 27-05-2025 | ISSUED FOR APPROVAL | EM09_A.pdf
15 | SE102 | ELEVATION VIEW | A | 27-05-2025 | ISSUED FOR APPROVAL | SE102_A.pdf
16 | SE103 | ELEVATION VIEW | A | 27-05-2025 | ISSUED FOR APPROVAL | SE103_A.pdf
17 | SE101 | ELEVATION VIEW | A | 27-05-2025 | ISSUED FOR APPROVAL | SE101_A.pdf
18 | EM03 | DOCK LEVELER | A | 27-05-2025 | ISSUED FOR APPROVAL | EM03_A.pdf
19 | SE105 | TYPICAL SECTIONS | A | 27-05-2025 | ISSUED FOR APPROVAL | SE105_A.pdf
20 | E101 | MASONRY | A | 27-05-2025 | ISSUED FOR APPROVAL | E101_A.pdf
21 | EM04 | SECTIONS | A | 27-05-2025 | ISSUED FOR APPROVAL | EM04_A.pdf
22 | SE104 | ELEVATION VIEW & DETAIL & SECTION | A | 27-05-2025 | ISSUED FOR APPROVAL | SE104_A.pdf
23 | 01C1001 | COLUMN DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01C1001_A.pdf
24 | EM02 | SECTIONS | A | 27-05-2025 | ISSUED FOR APPROVAL | EM02_A.pdf
25 | 01C1002 | COLUMN DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01C1002_A.pdf
26 | 01C1003 | COLUMN DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01C1003_A.pdf
27 | EM01 | BEARING PLATE FRAMING | A | 27-05-2025 | ISSUED FOR APPROVAL | EM01_A.pdf
28 | 01EM1000 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1000_A.pdf
29 | 01EM1001 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1001_A.pdf
30 | 01EM1002 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1002_A.pdf
31 | AB02 | ANCHOR | A | 27-05-2025 | ISSUED FOR APPROVAL | AB02_A.pdf
32 | 01EM1003 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1003_A.pdf
33 | EM06 | DETAIL & ELEVATION | A | 27-05-2025 | ISSUED FOR APPROVAL | EM06_A.pdf
34 | 01EM1005 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1005_A.pdf
35 | 01EM1004 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1004_A.pdf
36 | EM08 | BOLLARD | A | 27-05-2025 | ISSUED FOR APPROVAL | EM08_A.pdf
37 | 01EM1006 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1006_A.pdf
38 | 01EM1007 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1007_A.pdf
39 | 01EM1008 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1008_A.pdf
40 | 01EM1009 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1009_A.pdf
41 | 01EM1010 | EMBED ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1010_A.pdf
42 | 01EM1011 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1011_A.pdf
43 | 01EM1012 | EMBED PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1012_A.pdf
44 | 01EM1013 | 2 ANGLE FRAMES 01EM1013 | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1013_A.pdf
45 | 01EM1014 | 01EM1014 2 ANGLE FRAME Galv. 168 336 | A | 27-05-2025 | ISSUED FOR APPROVAL | 01EM1014_A.pdf
46 | 01GRT1000 | GRATING DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01GRT1000_A.pdf
47 | 01LP1 | LEVELING PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01LP1_A.pdf
48 | 01LP2 | LEVELING PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01LP2_A.pdf
49 | 01LP3 | LEVELING PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01LP3_A.pdf
50 | 01LP4 | LEVELING PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01LP4_A.pdf
51 | 01LP5 | LEVELING PLATE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01LP5_A.pdf
52 | 01M1000 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1000_A.pdf
53 | 01M1001 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1001_A.pdf
54 | 01M1002 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1002_A.pdf
55 | 01M1003 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1003_A.pdf
56 | 01M1004 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1004_A.pdf
57 | 01M1005 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1005_A.pdf
58 | 01M1006 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1006_A.pdf
59 | 01M1007 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1007_A.pdf
60 | 01M1008 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1008_A.pdf
61 | 01M1009 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1009_A.pdf
62 | 01M1010 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1010_A.pdf
63 | 01M1011 | ANGLE DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1011_A.pdf
64 | 01M1012 | CHANNEL DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1012_A.pdf
65 | EM05 | CRANE RAIL EMBED | A | 27-05-2025 | ISSUED FOR APPROVAL | EM05_A.pdf
66 | 01M1014 | CHANNEL DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1014_A.pdf
67 | 01M1013 | CHANNEL DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1013_A.pdf
68 | 01M1015 | ANGEL DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1015_A.pdf
69 | 01M1017 | PLATE DETAIL | 12 | PNT951140 | PLATE | 01M1017_A.pdf
70 | 01M1016 | THREADED ROD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1016_A.pdf
71 | 01M1018 | BOLLARD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1018_A.pdf
72 | 01M1019 | BOLLARD DETAIL | A | 27-05-2025 | ISSUED FOR APPROVAL | 01M1019_A.pdf
73 | EM07 | SECTION & ELEVATION | S | 5-20-25 | PROJ.NO.: 25012 | EM07_A.pdf
74 | AB01 | ANCHOR | 9 | 27-05-2025 | SOUTH FROM GRID 'E' IN LIEU OF EXTENTING 1-9" TO NORTH A GSV ISSUED FOR APPROVAL | AB01_A.pdf