## Transmittal
PROJECT NAME : STEEL |  |  | TRANSMITTAL NO: TR-011
FABRICATOR : INFRA |  |  | DATE: 03/17/2026
Sl. No. | Sheet No. | Drawing Title | Sent for Fabrication |  | Revision History
|  |  | REV# | DATE
11X17
1 | 02M1012 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE
2 | 03B1006 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE
3 | 03B1007 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE
4 | 03B1009 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE
5 | 03B1038 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
6 | 03B1039 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
7 | 03B1040 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
8 | 03B1041 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
9 | 03B1043 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE
10 | 03M1002 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
11 | 03M1003 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
12 | 03M1006 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
13 | 03M1007 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
14 | 04B1020 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
15 | 04B1025 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
16 | 04M1011 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
17 | 04M1024 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
18 | 04M1036 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE
19 | 04M1049 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE
20 | 04M1050 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE
21 | 04M1051 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE
22 | 06B1026 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
23 | 06B1029 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
24X36
24 | 02B1000 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
25 | 02B1038 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
26 | 02B1039 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
27 | 02B1042 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
28 | 02B1043 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
29 | 02B1044 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
30 | 02B1045 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
31 | 02B1046 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
32 | 03B1001 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
33 | 03C1006 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
34 | 03C1007 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
35 | 03C1017 | COLUMN DETAIL | 0 | 30-07-2025 | NOT IN USE
36 | 04B1012 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
37 | 04B1022 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
38 | 04B1023 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
39 | 04B1024 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
40 | 05B1016 | BEAM DETAIL | 1 | 30-07-2025 | REVISED AS NOTED
41 | 05B1017 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
42 | 05B1018 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
43 | 05B1019 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
44 | 05B1020 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
45 | 05B1021 | BEAM DETAIL | 1 | 30-07-2025 | REVISED AS NOTED
46 | 06B1023 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
47 | 06B1024 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
48 | 06B1027 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
49 | 06B1031 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
50 | 06B1032 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
51 | 06C1004 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION
25012-CLEVELAND BROTHERS MILESBURG_06C1001-REV
52 | 06C1001 | COLUMN DETAIL | 1 | 08-09-2025 | REVISED AS NOTED
8.5X11
53 | a12 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
54 | a14 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
55 | a15 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
56 | a16 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
57 | a75 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
58 | a120 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
59 | a121 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
60 | a215 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
61 | a279 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
62 | a291 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
63 | a295 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
64 | a297 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
65 | a332 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
66 | a333 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
67 | a340 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
68 | a341 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
69 | a344 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
70 | a359 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
71 | a360 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
72 | a361 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
73 | a363 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
74 | a365 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
75 | a366 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
76 | a367 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
77 | a368 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
78 | a918 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
79 | a983 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
80 | a984 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
81 | a1060 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
82 | a1094 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
83 | a1132 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
84 | a1133 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
85 | a1166 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
86 | bp8 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
87 | bp11 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
88 | bpl9 | BENT PLATE | 1 | 30-07-2025 | ISSUED FOR FABRICATION
89 | bpl13 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
90 | bpl94 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
91 | bpl102 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
92 | bpl1923 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
93 | pl55 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
94 | pl105 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
95 | pl120 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
96 | pl149 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
97 | pl160 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
98 | pl166 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
99 | pl172 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
100 | pl173 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
101 | pl183 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
102 | pl184 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
103 | pl198 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
104 | pl226 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
105 | pl285 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
106 | pl303 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
107 | pl342 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
108 | pl346 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
109 | pl393 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
110 | pl423 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
111 | pl460 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
112 | pl461 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
113 | pl954 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
114 | pl968 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
115 | pl970 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
116 | pl992 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
117 | pl995 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
118 | pl1062 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
119 | pl1065 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
120 | pl1067 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
121 | pl1118 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
122 | pl1124 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION
123 | pl1417 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION
124 | pl1568 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION