## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 06C1001 | COLUMN DETAIL | 1 | 08-09-2025 | REVISED AS NOTED | 06C1001_1.pdf
2 | a1166 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a1166_0.pdf
3 | a1094 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1094_0.pdf
4 | a120 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a120_0.pdf
5 | a1060 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a1060_0.pdf
6 | a14 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a14_0.pdf
7 | a15 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a15_0.pdf
8 | a1132 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a1132_0.pdf
9 | a121 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a121_0.pdf
10 | a1133 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1133_0.pdf
11 | a12 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a12_0.pdf
12 | a215 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a215_0.pdf
13 | a279 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a279_0.pdf
14 | a16 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a16_0.pdf
15 | a291 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a291_0.pdf
16 | a297 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a297_0.pdf
17 | a295 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a295_0.pdf
18 | a332 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a332_0.pdf
19 | a340 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a340_0.pdf
20 | a341 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a341_0.pdf
21 | a333 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a333_0.pdf
22 | a344 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a344_0.pdf
23 | a360 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a360_0.pdf
24 | a359 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a359_0.pdf
25 | a361 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a361_0.pdf
26 | a363 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a363_0.pdf
27 | a365 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a365_0.pdf
28 | a75 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a75_0.pdf
29 | a366 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a366_0.pdf
30 | a368 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a368_0.pdf
31 | a367 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a367_0.pdf
32 | pl1118 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1118_0.pdf
33 | pl1062 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl1062_0.pdf
34 | pl1065 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1065_0.pdf
35 | pl1067 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl1067_0.pdf
36 | pl1124 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1124_0.pdf
37 | pl105 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl105_0.pdf
38 | pl1417 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl1417_0.pdf
39 | pl1568 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1568_0.pdf
40 | pl120 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl120_0.pdf
41 | pl149 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl149_0.pdf
42 | pl172 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl172_0.pdf
43 | pl184 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl184_0.pdf
44 | pl160 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl160_0.pdf
45 | pl166 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl166_0.pdf
46 | pl198 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl198_0.pdf
47 | pl173 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl173_0.pdf
48 | pl183 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl183_0.pdf
49 | pl303 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl303_0.pdf
50 | pl226 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl226_0.pdf
51 | pl285 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl285_0.pdf
52 | a918 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a918_0.pdf
53 | a983 | ANGLE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | a983_0.pdf
54 | bp11 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp11_0.pdf
55 | bp8 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp8_0.pdf
56 | bpl13 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | bpl13_0.pdf
57 | bpl94 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | bpl94_0.pdf
58 | a984 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a984_0.pdf
59 | bpl102 | BENT PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | bpl102_0.pdf
60 | bpl1923 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1923_0.pdf
61 | bpl9 | BENT PLATE | 1 | 30-07-2025 | ISSUED FOR FABRICATION | bpl9_0.pdf
62 | pl342 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl342_0.pdf
63 | pl393 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl393_0.pdf
64 | pl346 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl346_0.pdf
65 | pl423 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl423_0.pdf
66 | pl460 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl460_0.pdf
67 | pl461 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl461_0.pdf
68 | pl954 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl954_0.pdf
69 | pl968 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl968_0.pdf
70 | pl970 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl970_0.pdf
71 | pl55 | PLATE | 0 | 30-07-2025 | ISSUED FOR FABRICATION | pl55_0.pdf
72 | pl992 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl992_0.pdf
73 | pl995 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl995_0.pdf
74 | 02B1046 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1046_0.pdf
75 | 02B1045 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1045_0.pdf
76 | 02B1038 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1038_0.pdf
77 | 02B1044 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1044_0.pdf
78 | 02B1042 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1042_0.pdf
79 | 03B1001 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03B1001_0.pdf
80 | 02B1039 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1039_0.pdf
81 | 02B1043 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1043_0.pdf
82 | 03C1017 | COLUMN DETAIL | 0 | 30-07-2025 | NOT IN USE | 03C1017_0.pdf
83 | 02B1000 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 02B1000_0.pdf
84 | 03C1006 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03C1006_0.pdf
85 | 05B1016 | BEAM DETAIL | 1 | 30-07-2025 | REVISED AS NOTED | 05B1016_1.pdf
86 | 04B1022 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1022_0.pdf
87 | 05B1017 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 05B1017_0.pdf
88 | 04B1024 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1024_0.pdf
89 | 05B1018 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 05B1018_0.pdf
90 | 04B1023 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1023_0.pdf
91 | 03C1007 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03C1007_0.pdf
92 | 05B1019 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 05B1019_0.pdf
93 | 02M1012 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE | 02M1012_0.pdf
94 | 05B1020 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 05B1020_0.pdf
95 | 04B1012 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1012_0.pdf
96 | 05B1021 | BEAM DETAIL | 1 | 30-07-2025 | REVISED AS NOTED | 05B1021_1.pdf
97 | 06B1023 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1023_0.pdf
98 | 03B1006 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE | 03B1006_0.pdf
99 | 06B1032 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1032_0.pdf
100 | 06B1031 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1031_0.pdf
101 | 03B1007 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE | 03B1007_0.pdf
102 | 06B1024 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1024_0.pdf
103 | 03B1009 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE | 03B1009_0.pdf
104 | 06B1027 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1027_0.pdf
105 | 03M1002 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 03M1002_0.pdf
106 | 03B1043 | BEAM DETAIL | 0 | 30-07-2025 | NOT IN USE | 03B1043_0.pdf
107 | 03M1003 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 03M1003_0.pdf
108 | 03M1006 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 03M1006_0.pdf
109 | 03B1038 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03B1038_0.pdf
110 | 03B1039 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03B1039_0.pdf
111 | 03M1007 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 03M1007_0.pdf
112 | 03B1041 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03B1041_0.pdf
113 | 03B1040 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 03B1040_0.pdf
114 | 04M1011 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1011_0.pdf
115 | 04M1024 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1024_0.pdf
116 | 04M1036 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1036_0.pdf
117 | 04M1049 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1049_0.pdf
118 | 04M1050 | BENT PLATE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1050_0.pdf
119 | 04M1051 | ANGLE DETAIL | 0 | 30-07-2025 | NOT IN USE | 04M1051_0.pdf
120 | 04B1020 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1020_0.pdf
121 | 04B1025 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 04B1025_0.pdf
122 | 06B1026 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1026_0.pdf
123 | 06B1029 | BEAM DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06B1029_0.pdf
124 | 06C1004 | COLUMN DETAIL | 0 | 30-07-2025 | ISSUED FOR FABRICATION | 06C1004_0.pdf