## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | SE211 | ELEVATION VIEW & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE211_0.pdf
2 | SE226 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE226_0.pdf
3 | SE225 | SECTIONS | OR | 05-09-2025 | GALVANIZED SURFACE AS REQ'D FOR FIELD WELDING. 0 GSV ISSUED FOR CONSTRUCTION | SE225_0.pdf
4 | SE223 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE223_0.pdf
5 | SE220 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE220_0.pdf
6 | SE228 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE228_0.pdf
7 | SE222 | SECTION & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE222_0.pdf
8 | SE227 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE227_0.pdf
9 | SE224 | SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE224_0.pdf
10 | E207 | ROOF FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E207_0.pdf
11 | SE221 | SECTION & DETAILS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE221_0.pdf
12 | E205 | CRANE RUNWAY | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E205_0.pdf
13 | E201 | MEZZANINE AND | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E201_0.pdf
14 | E202 | MEZZANINE | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E202_0.pdf
15 | E209 | ROOF MISC FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E209_0.pdf
16 | SE201 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE201_0.pdf
17 | E204 | CANOPY | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E204_0.pdf
18 | SE202 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE202_0.pdf
19 | E203 | LID & LUBE ROOM FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E203_0.pdf
20 | SE203 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE203_0.pdf
21 | SE204 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE204_0.pdf
22 | E206 | ROOF FRAMING | 1 | 11-06-2025 | A SRP ISSUED FOR APPROVAL | E206_0.pdf
23 | SE205 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE205_0.pdf
24 | SE229 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE229_0.pdf
25 | SE208 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE208_0.pdf
26 | SE206 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE206_0.pdf
27 | SE230 | TYPICAL SECTIONS | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE230_0.pdf
28 | E208 | ROOF MISC FRAMING | 6 | 11-06-2025 | x A SRP ISSUED FOR APPROVAL | E208_0.pdf
29 | E210 | ROOF MISC FRAMING | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | E210_0.pdf
30 | SE209 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE209_0.pdf
31 | SE207 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE207_0.pdf
32 | SE210 | ELEVATION VIEW | 0 | 05-09-2025 | ISSUED FOR CONSTRUCTION | SE210_0.pdf