## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name : celeveland |  |  |  | Client : SteelFab
Sl. No | Sheet No | Drawing Title | Sent for Approval |  | Sent for Fabrication |  | Remarks
|  |  | Rev A | Rev B | Rev 0 | Rev 1
DRAWINGS
1 | 07B1003 | BEAM DETAIL |  |  | Mar 11 2026 |  | ISSUED FOR FABRICATION
2 | 07GR1000 | GUARDRAIL DETAIL | Jun 16 2025 | Jan 27 2026 |  | Feb 23 2026 | ISSUED FOR FABRICATION
3 | 07GR1001 | GUARDRAIL DETAIL | Jun 16 2025 | Jan 27 2026 |  | Feb 23 2026 | ISSUED FOR FABRICATION
4 | 07GR1014 | GUARDRAIL DETAIL | Feb 23 2026 |  |  |  | ISSUED FOR FABRICATION
5 | 07M1010 | POST DETAIL | Feb 23 2026 |  |  |  | ISSUED FOR FABRICATION
6 | 07M1011 | PLATE DETAIL | Feb 23 2026 |  |  |  | NOT IN USE
7 | 07M1015 | ANGLE DETAIL |  |  | Mar 11 2026 |  | ISSUED FOR FABRICATION
8 | E703 | GUARDRAIL & LADDER PLAN | Jun 16 2025 | Jan 27 2026 |  | Feb 23 2026 | REVISED AS NOTED
9 | SE707 | GUARDRAIL ELEVATION VIEW | Jun 16 2025 | Jan 27 2026 |  | Feb 23 2026 | ISSUED FOR CONSTRUCTION
10 | SE707A | SECTIONS |  |  | Mar 11 2026 |  | ISSUED FOR CONSTRUCTION