## Transmittal
PROJECT NAME : CELEVELAND |  |  | TRANSMITTAL NO: TR-001
FABRICATOR : STEELFAB |  |  | DATE: 07/13/2026
Sl. No. | Sheet No. | Drawing Title | REV# | DATE | Revision History
DETAIL SHEET
1 | 07B1003 | BEAM DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION
2 | 07GR1000 | GUARDRAIL DETAIL | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
3 | 07GR1001 | GUARDRAIL DETAIL | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
4 | 07GR1014 | GUARDRAIL DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
5 | 07M1010 | POST DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
6 | 07M1011 | PLATE DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
7 | 07M1015 | ANGLE DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION
ERECTION SHEET
8 | E703 | GUARDRAIL & LADDER PLAN | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
9 | SE707 | GUARDRAIL ELEVATION VIEW | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
10 | SE707A | SECTIONS | 0 | Mar 11 2026 | ISSUED FOR CONSTRUCTION