## Transmittal
PROJECT NAME : SRRRRRRR |  |  | TRANSMITTAL NO: TR-001
FABRICATOR : STEEL FAB |  |  | DATE: 07/07/2026
Sl. No. | Sheet No. | Drawing Title | REV# | DATE | Revision History
DETAIL SHEET
1 | 07B1000 | BEAM DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
2 | 07B1001 | BEAM DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
3 | 07B1003 | BEAM DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION
4 | 07C1000 | COLUMN DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
5 | 07GR1000 | GUARDRAIL DETAIL | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
6 | 07GR1001 | GUARDRAIL DETAIL | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
7 | 07GR1005 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
8 | 07GR1006 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
9 | 07GR1007 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
10 | 07GR1008 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
11 | 07GR1009 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
12 | 07GR1010 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
13 | 07GR1011 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL
14 | 07GR1012 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
15 | 07GR1013 | GUARDRAIL DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL
16 | 07GR1014 | GUARDRAIL DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
17 | 07LDR1002 | 07LDR1002 LADDER DETAIL | 2 | Feb 12 2026 | REVISED AS NOTED
18 | 07M1009 | PLATE DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL
19 | 07M1010 | POST DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
20 | 07M1011 | PLATE DETAIL | A | Feb 23 2026 | ISSUED FOR APPROVAL
21 | 07M1014 | SAFETY GATE DETAIL | 0 | Mar 6 2026 | ISSUED FOR FABRICATION
22 | 07M1015 | ANGLE DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION
23 | 07STR1002 | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL
24 | 07STR1002A | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
25 | 07STR1002B | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
ERECTION SHEET
26 | E702 | DOCK STAIR FRAMING PLAN | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
27 | E703 | GUARDRAIL & LADDER PLAN | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
28 | E704 | HOSE ASSEMBLY DUSTCAAP (LADDER & HUARDRAIL PLAN) | 1 | Jan 27 2026 | ISSUED FOR CONSTRUCTION
29 | SE705 | STAIR ELEVATION VIEW | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
30 | SE706 | SECTIONS | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
31 | SE707 | GUARDRAIL ELEVATION VIEW | 1 | Feb 23 2026 | ISSUED FOR RE-APPROVAL
32 | SE707A | SECTIONS | 0 | Mar 11 2026 | ISSUED FOR CONSTRUCTION
33 | SE713 | LADDER ELEVATION VIEW | 1 | Jan 27 2026 | ISSUED FOR CONSTRUCTION