## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | SE707 | GUARDRAIL ELEVATION VIEW |  | Mar 11 2026 | ISSUED FOR CONSTRUCTION | SE707_1.pdf
2 | SE707A | SECTIONS | 0 | Mar 11 2026 | ISSUED FOR CONSTRUCTION | SE707A_0.pdf
3 | E703 | GUARDRAIL & LADDER PLAN |  | Mar 11 2026 | REVISED AS NOTED | E703_1.pdf
4 | 07M1011 | PLATE DETAIL |  | Mar 11 2026 | NOT IN USE | 07M1011_0.pdf
5 | 07GR1001 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1001_1.pdf
6 | 07B1003 | BEAM DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION | 07B1003_0.pdf
7 | 07GR1000 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1000_0.pdf
8 | SE713 | LADDER ELEVATION VIEW |  | Mar 6 2026 | REVISED AS NOTED | SE713_1.pdf
9 | 07M1015 | ANGLE DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION | 07M1015_0.pdf
10 | 07LDR1002 | 07LDR1002 LADDER DETAIL |  | Mar 6 2026 | NOT IN USE | 07LDR1002_2.pdf
11 | 07GR1014 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1014_0.pdf
12 | E704 | HOSE ASSEMBLY DUSTCAAP (LADDER & HUARDRAIL PLAN) |  | Mar 6 2026 | REVISED AS NOTED | E704_1.pdf
13 | 07M1010 | POST DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07M1010_0.pdf
14 | 07M1014 | SAFETY GATE DETAIL | 0 | Mar 6 2026 | ISSUED FOR FABRICATION | 07M1014_0.pdf