## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 07GR1005 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1005_1.pdf
2 | 07GR1006 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1006_1.pdf
3 | 07GR1007 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1007_1.pdf
4 | 07GR1008 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1008_1.pdf
5 | 07GR1009 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1009_1.pdf
6 | 07GR1012 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07GR1012_B.pdf
7 | 07GR1010 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1010_1.pdf
8 | SE706 | SECTIONS | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | SE706_B.pdf
9 | 07GR1013 | GUARDRAIL DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL | 07GR1013_A.pdf
10 | 07GR1011 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL | 07GR1011_B.pdf
11 | SE705 | STAIR ELEVATION VIEW | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | SE705_B.pdf