## Sheet1
PROJECT NAME : MARYLAND AVENUE PROJECT NO : 224009 FABRICATOR : IRON FABRICATION SERVICES,LLC. |  |  | TRANSMITTAL NO: #35 DATE: 11/14/2025
Sl. No. | Sheet No. | Drawing Title | Sent For Fabrication |  | REMARKS
|  |  | REV# | DATE
Erection Sheets - SOW #09
1 | E-09.00 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 9
2 | E-09.00A | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 9
3 | E-09.01 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 9
4 | E-09.02 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 9
5 | E-09.03 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 9
6 | E-09.04 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 9
7 | E-09.05 | SOW #09 LEVEL-03 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 9
Erection Sheets - SOW #10
1 | E-10.00 | SOW #10 LEVEL-04 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 10
2 | E-10.00A | SOW #10 LEVEL-04 DETAIL VIEW | 0 | 2025-11-14 | 10
3 | E-10.01 | SOW #10 LEVEL-04 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 10
4 | E-10.02 | SOW #10 LEVEL-04 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 10
5 | E-10.03 | SOW #10 LEVEL-04 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 10
6 | E-10.04 | SOW #10 LEVEL-04 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 10
Erection Sheets - SOW #11
1 | E-11.00 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 11
2 | E-11.00A | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 11
3 | E-11.00B | SOW #11 LEVEL-05 DETAIL VIEW | 0 | 2025-11-14 | 11
4 | E-11.01 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
5 | E-11.02 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
6 | E-11.03 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
7 | E-11.04 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
8 | E-11.05 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
9 | E-11.06 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
10 | E-11.07 | SOW #11 LEVEL-05 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 11
Erection Sheets - SOW #12
1 | E-12.00 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 12
2 | E-12.00A | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT FRAMING PLAN | 0 | 2025-11-14 | 12
3 | E-12.01 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 12
4 | E-12.02 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 12
5 | E-12.03 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 12
6 | E-12.04 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 12
7 | E-12.05 | SOW #12 LEVEL-06 NEW SLAB EXTENSION SUPPORT SECTIONS | 0 | 2025-11-14 | 12
Detail Sheets - SOW #09
1 | F-09.00 | FRAME DETAIL | 0 | 2025-11-14 | 9
2 | F-09.01 | FRAME DETAIL | 0 | 2025-11-14 | 9
3 | F-09.02 | FRAME & MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 9
4 | F-09.03 | BEAM & COLUMN DETAIL | 0 | 2025-11-14 | 9
5 | F-09.04 | BEAMS & ANGLE DETAIL | 0 | 2025-11-14 | 9
6 | F-09.05 | MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 9
7 | F-09.06 | MISC DETAIL | 0 | 2025-11-14 | 9
Detail Sheets - SOW #10
1 | F-10.00 | FRAME DETAIL | 0 | 2025-11-14 | 10
2 | F-10.01 | FRAME & MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 10
3 | F-10.02 | COLUMN & BEAM DETAIL | 0 | 2025-11-14 | 10
4 | F-10.03 | BEAM DETAIL | 0 | 2025-11-14 | 10
Detail Sheets - SOW #11
1 | F-11.00 | FRAME DETAIL | 0 | 2025-11-14 | 11
2 | F-11.01 | FRAME DETAIL | 0 | 2025-11-14 | 11
3 | F-11.02 | FRAME DETAIL | 0 | 2025-11-14 | 11
4 | F-11.03 | FRAME & MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 11
5 | F-11.04 | COLUMN & BEAM DETAIL | 0 | 2025-11-14 | 11
6 | F-11.05 | BEAM DETAIL | 0 | 2025-11-14 | 11
7 | F-11.06 | BEAM DETAIL | 0 | 2025-11-14 | 11
8 | F-11.07 | BEAM & MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 11
Detail Sheets - SOW #12
1 | F-12.00 | FRAME DETAIL | 0 | 2025-11-14 | 12
2 | F-12.01 | FRAME & MISCELLANEOUS DETAIL | 0 | 2025-11-14 | 12
3 | F-12.02 | COLUMN & BEAM DETAIL | 0 | 2025-11-14 | 12
4 | F-12.03 | MISC DETAIL | 0 | 2025-11-14 | 12