## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | E703 | GUARDRAIL & LADDER PLAN |  | Mar 11 2026 | REVISED AS NOTED | E703_1.pdf
2 | 07GR1001 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1001_1.pdf
3 | SE713 | LADDER ELEVATION VIEW |  | Mar 6 2026 | REVISED AS NOTED | SE713_1.pdf
4 | 07M1014 | SAFETY GATE DETAIL | 0 | Mar 6 2026 | ISSUED FOR FABRICATION | 07M1014_0.pdf
5 | E704 | HOSE ASSEMBLY DUSTCAAP (LADDER & HUARDRAIL PLAN) |  | Mar 6 2026 | REVISED AS NOTED | E704_1.pdf
6 | 07LDR1002 | 07LDR1002 LADDER DETAIL |  | Mar 6 2026 | NOT IN USE | 07LDR1002_2.pdf
7 | SE707A | SECTIONS | 0 | Mar 11 2026 | ISSUED FOR CONSTRUCTION | SE707A_0.pdf
8 | 07M1010 | POST DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07M1010_0.pdf
9 | 07GR1014 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1014_0.pdf
10 | 07B1003 | BEAM DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION | 07B1003_0.pdf
11 | 07GR1000 | GUARDRAIL DETAIL |  | Mar 11 2026 | ISSUED FOR FABRICATION | 07GR1000_0.pdf
12 | 07M1011 | PLATE DETAIL |  | Mar 11 2026 | NOT IN USE | 07M1011_0.pdf
13 | 07M1015 | ANGLE DETAIL | 0 | Mar 11 2026 | ISSUED FOR FABRICATION | 07M1015_0.pdf
14 | 07GR1005 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1005_1.pdf
15 | SE707 | GUARDRAIL ELEVATION VIEW |  | Mar 11 2026 | ISSUED FOR CONSTRUCTION | SE707_1.pdf
16 | 07GR1007 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1007_1.pdf
17 | 07GR1006 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1006_1.pdf
18 | 07GR1009 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1009_1.pdf
19 | 07GR1010 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1010_1.pdf
20 | 07GR1008 | GUARDRAIL DETAIL |  | Feb 5 2026 | ISSUED FOR FABRICARION | 07GR1008_1.pdf
21 | E702 | DOCK STAIR FRAMING PLAN | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | E702_B.pdf
22 | 07GR1011 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL | 07GR1011_B.pdf
23 | 07GR1012 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07GR1012_B.pdf
24 | 07GR1013 | GUARDRAIL DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL | 07GR1013_A.pdf
25 | SE706 | SECTIONS | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | SE706_B.pdf
26 | SE705 | STAIR ELEVATION VIEW | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | SE705_B.pdf
27 | 07STR1002A | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07STR1002A_B.pdf
28 | 07STR1002B | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07STR1002B_B.pdf
29 | 07B1000 | BEAM DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07B1000_B.pdf
30 | 07STR1002 | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL | 07STR1002_B.pdf
31 | 07C1000 | COLUMN DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07C1000_B.pdf
32 | 07M1009 | PLATE DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL | 07M1009_A.pdf
33 | 07B1001 | BEAM DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL | 07B1001_B.pdf