## Transmittal
PROJECT NAME : STEELLL |  |  | TRANSMITTAL NO: TR-001
FABRICATOR : STEEL FAB |  |  | DATE: 07/07/2026
Sl. No. | Sheet No. | Drawing Title | REV# | DATE | Revision History
DETAIL SHEET
1 | 07B1000 | BEAM DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
2 | 07GR1005 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
3 | 07GR1006 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
4 | 07GR1007 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
5 | 07GR1008 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
6 | 07GR1009 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
7 | 07GR1010 | GUARDRAIL DETAIL | 1 | Jan 27 2026 | ISSUED FOR FABRICATION
8 | 07GR1011 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL
9 | 07GR1012 | GUARDRAIL DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
10 | 07GR1013 | GUARDRAIL DETAIL | A | Feb 18 2026 | ISSUED FOR APPROVAL
11 | 07STR1002 | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR APPROVAL
12 | 07STR1002A | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
13 | 07STR1002B | STAIR DETAIL | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
ERECTION SHEET
14 | E702 | DOCK STAIR FRAMING PLAN | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
15 | SE705 | STAIR ELEVATION VIEW | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL
16 | SE706 | SECTIONS | B | Feb 18 2026 | ISSUED FOR RE-APPROVAL